## UCE Migration
Pilot Migration Plan UCE Infrastructure Environment
UCE Pilot Infrastructure Environment
Progreso general: 0% |  |  | 2026-03-23 | 2025-04-03 | Responsible
Id | Name | Progress | Start Date | End Date
1 | Preparation phase: | 0% | 2026-03-23 | 2025-03-24
1.1 | Creating the account | 0% | 2026-03-23 | 2026-03-23 | Gestnett/UCE/Huawei
1.2 | Partner Gestnett Console Association | 0% | 2026-03-23 | 2026-03-23 | Gestnett/UCE/Huawei
1.3 | Creating IAM Users | 0% | 2025-03-24 | 2025-03-24 | UCE
2 | Phase 0 - Network Settings: | 0% | 2025-03-26 | 2025-03-27
2.1 | Provisioning the VPC | 0% | 2025-03-26 | 2025-03-26 | UCE, Huawei (S)
2.2 | Security Group Definition | 0% | 2025-03-26 | 2025-03-26 | UCE, Huawei (S)
2.3 | VPN Configuration between Huawei Cloud On-Premise | 0% | 2025-03-26 | 2025-03-27 | UCE, Huawei (S)
2.4 | VPN Configuration between Huawei Cloud & Azure | 0% | 2025-03-26 | 2025-03-27 | Gestnett/UCE/Huawei
3 | Phase 1 - Migrate Moodle and other services | 0% | 2025-03-30 | 2025-04-02
3.1 | Install agent and start syncronization - UCEMOOD02 | 0% | 2025-03-30 | 2025-04-02 | Gestnett/UCE/Huawei
3.2 | Switchover Moodle application to Cloud | 0% | 2025-04-02 | 2025-04-02 | Gestnett/UCE/Huawei
4 | Phase 2 - Satisfaction Criteria Test: | 0% | 2025-04-01 | 2025-04-03
4.1 | Run tests previously defined | 0% | 2025-04-01 | 2025-04-02 | UCE
4.2 | Review test results | 0% | 2025-04-03 | 2025-04-03 | Gestnett/UCE/Huawei
4.3 | Make necessary adjustments based on the tests | 0% | 2025-04-03 | 2025-04-03 | Gestnett/UCE/Huawei
5 | Phase 3 - Integral migration: | 0% | 2025-04-03 | 2025-04-03
5.1 | Follow-up meeting to discuss pilot conclusion and next steps | 0% | 2025-04-03 | 2025-04-03 | Gestnett/UCE/Huawei
R = Responsible, S = Supporter
Formulas:
Start Date = [Start Date, row below]
End Date = [End Date, row below]

## VM Inventory
Servicios de computo
Server | Nombre | vCPU | Memoria RAM | Dirección IP privada | ¿Posee IP pública? | Almacenamiento por particiones TOTAL | Tipo Disco | SO | Versión SO | Promedio/Máximo de CPU | Promedio/Máximo RAM | Motor Base Datos (en caso de tener base de datos) | Servicio que corre
1 | [Ejemplo] Server Test | [Ejemplo] 8 | [Ejemplo] 32Gb |  |  | [Ejemplo] 128Gb / 256Gb | [Ejemplo] HDD / SSD | [Ejemplo] Windows | [Ejemplo] Server 2019 Standard | [Ejemplo] 35%/85% | [Ejemplo] 35%/85% | [Ejemplo] SQL | [Ejemplo] Web, BD, Moodle...
2 | ALUCEMOOD02 | 2 | 8GB | 10.0.16.5 | Si | 512GB | SSD | Linux | Linux (ubuntu 24.04) | Prom: 12%, Máx: 35.74% | Prom: 30%, Máx: 44% | MySQL | Moodle
3 | CEBUCEMOOD01 (Stopped) | 2 | 8GB | 10.0.17.4 | Si | 512GB | SSD | Linux | Linux (ubuntu 18.04) | Prom: 3%, Máx: 70.43% | Prom: 24%, Máx: 27% | MySQL | Moodle
4 | CMUCE01 | 2 | 8GB | 172.17.64.10 | Si | 30GB | SSD | Linux | Linux (ubuntu 20.04) | Prom: 3.5%, Máx: 52.7% | Prom: 55%, Máx: 58% |  | Web
5 | EgresadosMau02 | 2 | 8GB | 10.3.0.6 | Si | 30GB | SSD | Linux | Linux (debian 10.13) | Prom: 5%, Máx: 90% | Prom: 75%, Máx: 80% | MySQL | MAUTIC
6 | EGRESADOSWP02 | 2 | 8GB | 10.3.0.4 | Si | 30GB | SSD | Linux | Linux (ubuntu 24.04) | Prom: 69%, Máx: 99% | Prom: 85%, Máx: 95% | MySQL | WordPress
7 | REDMINEPNUD03 | 2 | 8GB | 10.2.0.4 | Si | 30GB | SSD | Linux | Linux (debian 10.13) | Prom: 1%, Máx: 15.77% | Prom: 20%, Máx: 23% | MySQL | Redmine
8 | SRVCIDIIA | 8 | 16GB | 10.4.0.4 | Si | 256GB | SSD | Linux | Linux (debian 12) | Prom: 2%, Máx: 27% | Prom: 92%, Máx: 97% | MySQL | Web
9 | UCEAZBE (Stopped) | 1 | 3.5GB | 172.17.64.6 | Si | 64GB | SSD | Linux |  | 0 | 0
10 | UCEAZBIB01 | 4 | 16GB | 172.17.64.5 | Si | 30GB | HDD | Linux | Linux (ubuntu 17.10) | Prom: 58%, Máx: 95% | Prom: 13%, Máx: 99% | MySQL | KOHA
11 | UCEAZCEGODEL | 1 | 3.5GB | 172.17.64.21 | Si | 32GB | SSD | Linux | Linux (ubuntu 24.04) | Prom: 1%, Máx: 71% | Prom: 43%, Máx: 56% | MySQL | WordPress
12 | UCEAZCOSTO | 2 | 8GB | 172.17.64.14 | Si | 64GB | SSD | Linux | Linux (ubuntu 20.04) | Prom: 3%, Máx: 23% | Prom: 40%, Máx: 41% |  | Web
13 | UCEAZDATAGATEWAY | 2 | 8GB | 172.17.64.16 | Si | 127GB | SSD | Windows | Windows (Windows Server 2019 Datacenter) | Prom: 3%, Máx: 61% | Prom: 68GB, Máx: 82% |  | Gateway Power Automate
14 | UCEAZDC02 | 2 | 8GB | 172.17.64.12 | No | 127GB | SSD | Windows | Windows (Windows Server 2019 Datacenter) | Prom: 20%, Máx: 94% | Prom: 88%, Máx: 97% |  | AD Domain Controller
15 | UCEAZEXP01 | 2 | 8GB | 172.17.64.13 | Si | 64GB | SSD | Linux | Linux (ubuntu 22.04) | Prom: 2%, Máx: 72% | Prom: 20%, Máx: 25% | MySQL | Redmine
16 | UCEAZFORMS | 1 | 3.5GB | 172.17.64.4 | Si | 64GB | SSD | Linux | Linux (ubuntu 24.04) | Prom: 1%, Máx: 76% | Prom: 40%, Máx: 42% | MySQL | Limesurvey
17 | UCEAZFRONTEND | 2 | 8GB | 172.17.64.18 | Si | 64GB | SSD | Linux | Linux (ubuntu 24.04) | Prom: 3%, Máx: 71% | Prom: 30%, Máx: 47% | MySQL | WordPress
18 | UCEAZGLITCHTIP | 1 | 3.5GB | 172.17.64.8 | Si | 256GB | SSD | Linux | Linux (ubuntu 24.04) | Prom: 70%, Máx: 99% | Prom: 40%, Máx: 42% | MySQL | Glithctip
19 | UCEAZIDIOMAS | 2 | 8GB | 10.1.0.6 | Si | 256GB | SSD | Linux | Linux (ubuntu 24.04) | Prom: 3%, Máx: 99% | Prom: 30%, Max: 48% | MySQL | Moodle
20 | UCEAZINVOICENINJA (Stopped) | 2 | 8GB | 172.17.64.19 | Si | 128GB | SSD | Linux | Linux (ubuntu 24.04) | Prom: 14%, Máx: 76% | Prom: 45%, Max: 49%
21 | UCEAZMODREF | 4 | 16GB | 172.17.64.15 | Si | 256GB | HDD | Windows | Windows (Windows Server 2019 Datacenter) | Prom: 3%, Máx: 79% | Prom: 50%, Máx: 99% | MySQL | Moodle
22 | UCEAZREP01 | 2 | 14GB | 172.17.64.29 | Si | 127GB | SSD | Windows | Windows (Windows Server 2016 Datacenter) | Prom: 6%, Max: 94% | Prom: 33%, Max: 50% |  | Reporting services
23 | UCEAZREP02 (Stopped) | 4 | 14GB | 172.17.64.30 | No | 127GB | SSD | Windows | Windows (Windows Server 2016 Datacenter) | 0 | 0 |  | Reporting services
24 | UCEAZREVISTAUC | 2 | 8GB | 10.2.0.4 | Si | 30GB | SSD | Linux | Linux (ubuntu 24.04) | Prom: 2%, Máx: 63% | Prom: 30%, Máx: 33% | MySQL | Open Journal System (OJS)
25 | UCEAZRRHHMOD | 2 | 4GB | 172.17.64.11 | Si | 64GB | SSD | Linux | Linux (ubuntu 20.04) | Prom: 2%, Máx: 54% | Prom: 52%, Max: 68% | MySQL | Moodle
26 | UCEAZSP01 | 4 | 16GB | 172.17.64.36 | Si | 200GB | SSD | Windows | Windows (Windows Server 2016 Datacenter) | Prom: 30%, Max: 94% | Prom: 50%, Máx: 61% |  | Sharepoint
27 | UCEAZSP2013-5 | 4 | 28GB | 172.17.64.49 | Si | 500GGB | HDD | Windows | Windows (Windows Server 2008 R2 Datacenter) | Prom: 6%, Max: 74% | Prom: 40%, Max: 49% |  | Sharepoint
28 | UCEAZSQL01 | 4 | 16GB | 172.17.64.26 | No | 3,400 GB | SSD | Windows | Windows (Windows Server 2016 Datacenter) | Prom: 10%, Max: 88% | Prom: 92%, Máx: 97% | SQL Server | BD
29 | UCEAZSQL02 | 8 | 32GB | 172.17.64.27 | No | 127GB | SSD | Windows | Windows (Windows Server 2016 Datacenter) | Prom: 25%, Max: 94% | Prom: 92%, Máx: 99% | SQL Server | BD
30 | UCEAZSQL03 (Stopped) | 8 | 28GB | 172.17.64.28 | No | 127GB | SSD | Windows | Windows (Windows Server 2016 Datacenter) | 0 | 0 | SQL Server | BD
31 | UCEAZWEB01 (Stopped) | 1 | 3.5GB | 172.17.64.23 | Si | 127GB | SSD | Windows | Windows (Windows Server 2016 Datacenter) | 0 | 0 |  | Web
32 | UCEAZWEB02 | 4 | 14GB | 172.17.64.24 | Si | 150GB | SSD | Windows | Windows (Windows Server 2016 Datacenter) | Prom: 4%, Max: 85% | Prom: 40%, Max: 88% |  | Web
33 | UCEMOOD01 (Stopped) | 2 | 8GB | 10.1.0.7 | Si | 3,122GB | HDD | Linux | Linux (ubuntu 18.04) | 0 | 0 | MySQL | Moodle
34 | UCEMOOD02 (migrar en 1era. fase) | 8 | 32GB | 172.17.64.17 | Si | 3,122GB | SSD | Linux | Linux (ubuntu 24.04) | Prom: 17%, Max: 99% | Prom: 80%, Máx: 99% | MySQL | Moodle
35 | UCEAZFINANCIERO | 2 | 8GB | 172.17.64.7 | Si | 64GB | SSD | Linux | Linux (ubuntu 24.04) | Prom: 10.44%, Max: 90.6% | Prom: 25%, Max: 29% |  | Web
36 | UCEAZSQL-SISPEDRO | 2 | 8GB | 172.17.64.34 | No | 127GB | SSD | Windows | Windows (Windows Server 2016 Datacenter) | Prom: 3.45%, Max: 93.43% | prom: 42%, Max: 57% | SQL Server | BD
Note on A1: La primera linea es un ejemplo.

## Whole Infra Quotation
CALCULADORA DE SERVICIOS
Price Calculator Mar 20, 2026
Required | Service | Description | Region | AZ | Billing Mode | Purchase Amount | Unit | Quantity | Specifications | Unit Price (USD) | Yearly Price (USD) | Monthly Price (USD)
ALUCEMOOD02 | Elastic Cloud Server 1 | ALUCEMOOD02 | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Ubuntu ¦ Ubuntu 22.04 server 64bit; x86 ¦ General computing ¦ s7n.large.4 ¦ 2 vCPUs ¦ 8GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 512GB; | 972.95 | 972.95 | 81.0792
CMUCE01 | Elastic Cloud Server 3 | CMUCE01 | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Ubuntu ¦ Ubuntu 22.04 server 64bit; x86 ¦ General computing ¦ x0.2u.8g ¦ 2 vCPUs ¦ 8GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 100GB; | 409.92 | 409.92 | 34.16
EgresadosMau02 | Elastic Cloud Server 4 | EgresadosMau02 | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Debian ¦ Debian 11.1.0 64bit; x86 ¦ General computing ¦ s7n.large.4 ¦ 2 vCPUs ¦ 8GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 100GB; | 503.76 | 503.76 | 41.98
EGRESADOSWP-RESTAURADA-2 | Elastic Cloud Server 5 | EGRESADOSWP-RESTAURADA-2 | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Debian ¦ Debian 11.1.0 64bit; x86 ¦ General computing ¦ x0.2u.8g ¦ 2 vCPUs ¦ 8GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 100GB; | 409.92 | 409.92 | 34.16
REDMINEPNUD03 | Elastic Cloud Server 6 | REDMINEPNUD03 | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Debian ¦ Debian 11.1.0 64bit; x86 ¦ General computing ¦ x0.2u.8g ¦ 2 vCPUs ¦ 8GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 100GB; | 409.92 | 409.92 | 34.16
SRVCIDIIA | Elastic Cloud Server 7 | SRVCIDIIA | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Debian ¦ Debian 11.1.0 64bit; x86 ¦ General computing ¦ s7n.2xlarge.2 ¦ 8 vCPUs ¦ 16GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 256GB; | 1598.57 | 1598.57 | 133.2142
UCEAZBIB01 | Elastic Cloud Server 8 | UCEAZBIB01 | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Debian ¦ Debian 11.1.0 64bit; x86 ¦ General computing ¦ s7n.xlarge.4 ¦ 4 vCPUs ¦ 16GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 100GB; | 892.68 | 892.68 | 74.39
UCEAZCEGODEL | Elastic Cloud Server 9 | UCEAZCEGODEL | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Ubuntu ¦ Ubuntu 22.04 server 64bit; x86 ¦ General computing ¦ x0.1u.4g ¦ 1vCPU ¦ 4GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 100GB; | 261.96 | 261.96 | 21.83
UCEAZCOSTO | Elastic Cloud Server 10 | UCEAZCOSTO | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Ubuntu ¦ Ubuntu 22.04 server 64bit; x86 ¦ General computing ¦ x0.2u.8g ¦ 2 vCPUs ¦ 8GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 100GB; | 409.92 | 409.92 | 34.16
UCEAZDATAGATEWAY | Elastic Cloud Server 11 | UCEAZDATAGATEWAY | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Private Image: Windows Server (BYOL) 64 bit; x86 ¦ General computing ¦ x0.2u.8g ¦ 2 vCPUs ¦ 8GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 127GB; | 440.67 | 440.67 | 36.7225
UCEAZDC02 | Elastic Cloud Server 12 | UCEAZDC02 | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Private Image: Windows Server (BYOL) 64 bit; x86 ¦ General computing ¦ s7n.large.4 ¦ 2 vCPUs ¦ 8GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 127GB; | 534.51 | 534.51 | 44.5425
UCEAZEXP01 | Elastic Cloud Server 13 | UCEAZEXP01 | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Ubuntu ¦ Ubuntu 22.04 server 64bit; x86 ¦ General computing ¦ x0.2u.8g ¦ 2 vCPUs ¦ 8GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 100GB; | 409.92 | 409.92 | 34.16
UCEAZFORMS | Elastic Cloud Server 14 | UCEAZFORMS | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Ubuntu ¦ Ubuntu 22.04 server 64bit; x86 ¦ General computing ¦ x0.1u.4g ¦ 1vCPU ¦ 4GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 100GB; | 261.96 | 261.96 | 21.83
UCEAZFRONTEND | Elastic Cloud Server 15 | UCEAZFRONTEND | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Ubuntu ¦ Ubuntu 22.04 server 64bit; x86 ¦ General computing ¦ x0.2u.8g ¦ 2 vCPUs ¦ 8GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 100GB; | 409.92 | 409.92 | 34.16
UCEAZGLITCHTIP | Elastic Cloud Server 16 | UCEAZGLITCHTIP | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Ubuntu ¦ Ubuntu 22.04 server 64bit; x86 ¦ General computing ¦ x0.1u.4g ¦ 1vCPU ¦ 4GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 256GB; | 439.61 | 439.61 | 36.6342
UCEAZIDIOMAS | Elastic Cloud Server 17 | UCEAZIDIOMAS | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Ubuntu ¦ Ubuntu 22.04 server 64bit; x86 ¦ General computing ¦ x0.2u.8g ¦ 2 vCPUs ¦ 8GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 256GB; | 587.57 | 587.57 | 48.9642
UCEAZMODREF | Elastic Cloud Server 19 | UCEAZMODREF | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Private Image: Windows Server (BYOL) 64 bit; x86 ¦ General computing ¦ x0.4u.16g ¦ 4 vCPUs ¦ 16GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 256GB; | 883.73 | 883.73 | 73.6442
UCEAZREP01 | Elastic Cloud Server 20 | UCEAZREP01 | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Private Image: Windows Server (BYOL) 64 bit; x86 ¦ General computing ¦ x0.2u.12g ¦ 2 vCPUs ¦ 12GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 127GB; | 474.87 | 474.87 | 39.5725
UCEAZREVISTAUC | Elastic Cloud Server 21 | UCEAZREVISTAUC | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Ubuntu ¦ Ubuntu 22.04 server 64bit; x86 ¦ General computing ¦ x0.2u.8g ¦ 2 vCPUs ¦ 8GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 100GB; | 409.92 | 409.92 | 34.16
UCEAZRRHHMOD | Elastic Cloud Server 22 | UCEAZRRHHMOD | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Ubuntu ¦ Ubuntu 22.04 server 64bit; x86 ¦ General computing ¦ x0.2u.4g ¦ 2 vCPUs ¦ 4GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 100GB; | 375.84 | 375.84 | 31.32
UCEAZSP01 | Elastic Cloud Server 23 | UCEAZSP01 | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Private Image: Windows Server (BYOL) 64 bit; x86 ¦ General computing ¦ x0.4u.16g ¦ 4 vCPUs ¦ 16GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 200GB; | 819.96 | 819.96 | 68.33
UCEAZSP2013-5 | Elastic Cloud Server 24 | UCEAZSP2013-5 | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Private Image: Windows Server (BYOL) 64 bit; x86 ¦ General computing ¦ x0.4u.32g ¦ 4 vCPUs ¦ 32GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 500GB; | 1298.28 | 1298.28 | 108.19
UCEAZSQL01 | Elastic Cloud Server 25 | UCEAZSQL01 | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Private Image: Windows Server (BYOL) 64 bit; x86 ¦ General computing ¦ s7n.xlarge.4 ¦ 4 vCPUs ¦ 16GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 100GB; General Purpose SSD ¦ 3400GB; | 4764.6 | 4764.6 | 397.05
UCEAZSQL02 | Elastic Cloud Server 26 | UCEAZSQL02 | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Private Image: Windows Server (BYOL) 64 bit; x86 ¦ General computing ¦ s7n.2xlarge.4 ¦ 8 vCPUs ¦ 32GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 127GB; | 1702.11 | 1702.11 | 141.8425
UCEAZWEB02 | Elastic Cloud Server 27 | UCEAZWEB02 | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Private Image: Windows Server (BYOL) 64 bit; x86 ¦ General computing ¦ x0.4u.16g ¦ 4 vCPUs ¦ 16GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 150GB; | 763.02 | 763.02 | 63.585
UCEMOOD02 | Elastic Cloud Server 28 | UCEMOOD02 | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Ubuntu ¦ Ubuntu 22.04 server 64bit; x86 ¦ General computing ¦ x0.8u.32g ¦ 8 vCPUs ¦ 32GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 128GB; General Purpose SSD ¦ 3122GB; | 4885.5 | 4885.5 | 407.125
App Service | Elastic Cloud Server 29 | App Service | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Private Image: Windows Server (BYOL) 64 bit; x86 ¦ General computing ¦ x0.1u.2g ¦ 1vCPU ¦ 2GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 50GB; | 187.5 | 187.5 | 15.625
UCEAZFINANCIERO | Elastic Cloud Server 30 | UCEAZFINANCIERO | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Ubuntu ¦ Ubuntu 22.04 server 64bit; x86 ¦ General computing ¦ x0.2u.8g ¦ 2 vCPUs ¦ 8GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 70GB; | 375.76 | 375.76 | 31.3133
UCEAZSQL-SISPEDRO | Elastic Cloud Server 31 | UCEAZSQL-SISPEDRO | LA-Mexico City2 | General AZ | RI | 1 |  | 1 | Private Image: Windows Server (BYOL) 64 bit; x86 ¦ General computing ¦ x0.2u.8g ¦ 2 vCPUs ¦ 8GiB ¦ No Upfront ¦ 1 Year; General Purpose SSD ¦ 150GB; | 466.86 | 466.86 | 38.905
Server Backup | Cloud Backup and Recovery 1 | Cloud Backup and Recovery | LA-Mexico City2 | General AZ | Pay-per-use | 8760 | hours | 1 | Server backup vault ¦ 22000GB; | 9636 | 9636 | 803
Object Storage | Object Storage Service 1 | Object Storage Service | LA-Mexico City2 | General AZ | Pay-per-use | 12 | month | 1 | Standard ¦ 150GB ¦ Multi-AZ storage ¦ Object storage ¦ Storage Duration:12month; 0GB; 1000x 10,000 requests; 1000x 10,000 requests; 1000x 1,000 requests; 0GB; 0GB; | 95.8 | 1149.6 | 95.8
| Object Storage Service 2 | Object Storage Service | LA-Mexico City2 | General AZ | Pay-per-use | 12 | month | 1 | Infrequent Access ¦ 750GB ¦ Multi-AZ storage ¦ Object storage ¦ Storage Duration:12month; 100GB; Urgent: 1-5 minutes ¦ 0GB; 1000x 1,000 requests; 1000x 1,000 requests; 1000x 1,000 requests; 4x 10,000 requests; 0GB; 0GB; | 133 | 1596 | 133
Connectivity | Virtual Private Network 1 | Virtual Private Network | LA-Mexico City2 | General AZ | Pay-per-use | 8760 | Hours | 1 | Professional 1 ¦ 1PCSVPN Connection Groups; Traffic ¦ 1GB; Traffic ¦ 1GB; | 2890.96 | 2890.96 | 240.9133
| Elastic IP 1 | Elastic IP | LA-Mexico City2 | General AZ | Pay-per-use | 8760 | hours | 1 | Dedicated ¦ Dynamic BGP ¦ Traffic ¦ 48TB; 1 ; | 3869.46 | 3869.46 | 322.455
Security | Host Security Service 1 | Host Security Service | LA-Mexico City2 | General AZ | Monthly | 12 | month | 29 | Premium; | 13.8 | 4802.4 | 400.2
Support Plan | Support Plans 1 | Support Plans | LA-Mexico City2 | General AZ | Monthly | 12 | month | 1 | Business ¦ 4400USD/month; | 440 | 5280 | 440
Total Price | [9 empty] | 26361.71 | 26361.71 | 4632.1775
The preceding price is for reference only and may vary from the final price in your bill
Monthly Price | 4632.1775
Huawei Confidential

## Pilot Infra Quotation
CALCULADORA DE SERVICIOS
Price Calculator Mar 20, 2026
Required | Service | Description | Region | AZ | Billing Mode | Purchase Amount | Unit | Quantity | Specifications | Unit Price (USD) | Yearly Price (USD) | Monthly Price (USD)
UCEMOOD02 | Elastic Cloud Server 28 | UCEMOOD02 | LA-Mexico City2 | General AZ | Pay-per-use | 730 | hours | 1 | x86 ¦ General computing ¦ x0.8u.32g ¦ 8 vCPUs ¦ 32GiB; Ubuntu ¦ Ubuntu 22.04 server 64bit; General Purpose SSD ¦ 128GB; General Purpose SSD ¦ 3122GB; | 460.27 | 5523.24 | 460.27
Server Backup | Cloud Backup and Recovery 1 | Cloud Backup and Recovery | LA-Mexico City2 | General AZ | Pay-per-use | 8760 | hours | 1 | Server backup vault ¦ 12000GB; | 5256 | 5256 | 438
Connectivity | Virtual Private Network 1 | Virtual Private Network | LA-Mexico City2 | General AZ | Pay-per-use | 8760 | Hours | 1 | Professional 1 ¦ 1PCSVPN Connection Groups; Traffic ¦ 1GB; Traffic ¦ 1GB; | 2890.96 | 2890.96 | 240.9133
| Elastic IP 1 | Elastic IP | LA-Mexico City2 | General AZ | Pay-per-use | 8760 | hours | 1 | Dedicated ¦ Dynamic BGP ¦ Traffic ¦ 24TB; 1 ; | 1977.11 | 1977.11 | 164.7592
Security | Host Security Service 1 | Host Security Service | LA-Mexico City2 | General AZ | Monthly | 1 | month | 1 | Premium; | 13.8 | 165.6 | 13.8
Support Plan | Support Plans 1 | Support Plans | LA-Mexico City2 | General AZ | Monthly | 12 | month | 1 | Business ¦ 1300USD/month; | 130 | 1560 | 130
Total Price | [9 empty] | 460.27 | 5523.24 | 1447.7425
The preceding price is for reference only and may vary from the final price in your bill
Monthly Price | 1447.7425
Huawei Confidential